## PBS SAP
Niveau | ID | SAP
1 | 1 | Finance module
2 | 1.1 | General accounting
2 | 1.1 | Customer accounting
2 | 1.2 | Accounts payable
2 | 1.1 | Fixed assets accounting
2 | 1.1 | Cash management and bank accounting
2 | 1.2 | Travel Management
2 | 1.1 | Consolidations
1 | 2 | Purchasing module
2 | 2.1 | Requirements planning
2 | 2.2 | Procurement management
2 | 2.3 | Order management
2 | 2.4 | Billing management
2 | 2.5 | Subcontracting management
1 | 3 | Sales module
2 | 3.1 | Sales support
2 | 3.2 | Bid management
2 | 3.3 | Shipment management
2 | 3.4 | Billing management
1 | 4 | Logistics module
2 | 4.2 | Goods receipt
2 | 4.3 | Inventory
2 | 4.4 | Resource planning
2 | 5 | Production support module
2 | 5.1 | Production planning
2 | 5.3 | Capacity planning
2 | 5.4 | Production monitoring
2 | 5.6 | Technical data management
The PBS (Product Breakdown Structure)
is a process for breaking down the project delivrables into sub-products.
In our example, the product, which is the SAP software package, is broken down into sub-products, called "modules", namely
* Finance module
* Purchasing module
* Sales module
* Logistics module
* Production support module
Learn more about the PBS In this article.

## WBS SAP
Level | ID | Tasks | Workload
1 | 1 | Initiation | 18
2 | 1.0 | Opportunity and approval study | 10
2 | 1.1 | Preparation of the Project Charter - Justification | 1
2 | 1.2 | Cost / time estimate | 5
2 | 1.3 | Drafting the Project Charter | 1
3 | 1.3.1 | Initial risk assessment | 2
2 | 1.4 | Approval of the Project Charter | 1
1 | 2 | Planning | 102
2 | 2.1 | General conception | 20
2 | 2.2 | Drafting specifications | 22
2 | 2.3 | Detailed conception | 15
3 | 2.3.1 | DFS (detailed functional specifications) finance modules
3 | 2.3.2 | DFS purchasing modules
3 | 2.3.3 | DFS sales modules
3 | 2.3.4 | DFS logistics modules
3 | 2.3.5 | DFS production support modules
2 | 2.4 | Planning development | 22
2 | 2.5 | Drafting the communication plan | 22
3 | 2.5.1 | Training strategy | 10
3 | 2.5.2 | Governance scheme | 8
2 | 2.6 | Approval of specifications, communication plan, project plan and planning | 1
1 | 3 | Execution | 217
2 | 3.1 | Parameterization and unit tests | 65
2 | 3.2 | Master Data settings and corrections | 65
2 | 3.3 | Parameter setting, programming and production test | 65
2 | 3.4 | System tests, corrections and validation | 20
2 | 3.5 | Official validation by users | 1
2 | 3.6 | Validation of the phase by the management committee | 1
1 | 4 | Control and monitoring | 184
2 | 4.1 | Integration and consolidation tests | 21
2 | 4.2 | Integration and consolidation tests, system validation | 10
2 | 4.3 | User training | 11
2 | 4.4 | Preparation and validation of pre-production environment | 20
2 | 4.5 | Deployment | 0
2 | 4.6 | Failover and validation | 0
2 | 4.7 | Master Data validation | 0
2 | 4.8 | User validation | 0
2 | 4.9 | Productive start-up decision | 0
2 | 4.10 | Productive start | 0
2 | 4.11 | Project monitoring, documentation and corrections | 38
2 | 4.12 | Master Data Corrections | 38
2 | 4.13 | User tracking | 38
2 | 4.14 | Month-end | 4
2 | 4.15 | PV Acknowledgment of receipt | 4
1 | 5 | Closing | 30
2 | 5.1 | List of corrections | 10
2 | 5.2 | Documentation lessons learned Project | 10
2 | 5.3 | Correction plan | 10
2 | 5.4 | Closing meeting | 0
The WBS (Work Breakdown Structure) is the process of breaking down a project, from the PBS, into achievable tasks.
The tasks related to project management are grouped by management phase:
* Initiation
* Planning
* Execution
* Control and monitoring
* Closing
Lean more about the WBS In this article.

## Data
Level
1
2
3
4
5