## Slide 1
Steering Committee Support Presentation
SAP30/CMRL
On 20/10/2022

## Slide 2: Agenda
  Previous STEERCO decisions
  Progress Status
  Project performance
    Budget review
    Schedule review
    Risk review
    KPIs status
    Required decisions
  Change Requests Validation
  Questions/Answers
  Next Meetings

## Slide 3: Previous STEERCO decisions
Decision 1
  Master Data resource increase approval
Decision 2
  CRM implementation approval in January 2023
Decision 3
  Involvement of internal auditors in testing
Decision 4
  Approval of external communication plan

## Slide 4: Progress Status
Main difficulties encountered
  Poor quality of certain data requiring a lot of correction work
  Wide range of fixed assets
  Important differences in chart of accounts
  Product file to be cleaned
To be done
  Before integration tests
    Review the scenarios and complete the examples
    Distribute tests by user expertise
    Finalize training materials
  Before integration tests
    Adapt the consolidation test plan
    Confirm the training plan and send the invitations
    Complete the tests to adapt them to the pre-production environment
Done
  Parameterization and unit testing of domains
      Finance
      Sales
      Purchasing
      Logistics
      Production
      Master Data
  Correction of identified issues
  Datasets for integration testing
  Preparation of integration / consolidation scenarios

## Slide 5: Project performance: Budget review simplified
Chart: Budget SAP30/CMRL End of September 2022
| Total | Réel | Planifié à cette date
sept-21 | 420000 | 182500 | 184000
Notes: Possible de détailler la performance par services/périmètres. Par exemple splitter cet indicateur entre finances/logistique/achats etc.

## Slide 6: Project performance: Earned value analysis ½ *
See "Budget monitoring report" for more details

## Slide 7: Project performance: Earned value analysis 2/2 *
Chart: Valeur Acquise SAP30/CMRL
| 44256 | 44287 | 44317 | 44348 | 44378 | 44409 | 44440 | 44470 | 44501 | 44531 | 44562 | 44593
Valeur Planifiée (VP) | 5000 | 22000 | 39000 | 56000 | 94000 | 132000 | 170000 | 181500 | 252000 | 321000 | 344000 | 346000
Valeur Acquise (VA) | 3000 | 18880 | 35760 | 53000 | 93660 | 131320 | 170000 | 181500 | 248800 | 333000 | 344000 | 346000
Coût Réel (CR) | 4000 | 22000 | 39000 | 55500 | 93500 | 131500 | 169500 | 181000 | 261000 | 335000 | 355000 | 357000
See "Budget monitoring report" for more details

## Slide 8: Performance de projet : Revue du Planning
Project performance: Schedule review
The movements of the past period :
  Delivery of parameterized and tested systems in all areas of work
  Data cleaning and corrections
  Collection of interface requirements
  Collection of CRM requirements
  Validation by key users
  Planned for the following period:
  Integration test
  Consolidation test
  Finalized training materials
  Detailed data failover plan
  Detailed acceptance test plan for solutions in all areas of work
  Preparation of the functional and operational changeover plan
Notes: Possible de garder en référence la Baseline.
Et donc afficher le planning original et le planning réel, pour mettre en évidence les glissement de planning (en retard comme en avance d’ailleurs)

## Slide 9: Project risk review
Description | severity | Probability | Criticality | Consequence if happens | Preventive Actions | Corrective Actions
Status-Quo | Catastrophic | Unlikely | Very critical | Cost, deadline, strategy | Start of the SAP CMRL project | Start of the SAP CMRL project
Control/Audit | Severe | Likely | Very critical | Cost and deadlines | Accelerated SAP implementation | Agreements with auditors
Lack of support or interest | Major | Unlikely | Critical | Deadlines and quality | Communication plan and assignment of a responsible change | Transparent communication
Dependencies between projects | Major | Likely | Critical | Cost, deadlines, strategy | SAP project and CMRL expansion project in the same portfolio | Change management
Deadline December 2023 | Major | Unlikely | Moderated | Cost, deadlines, strategy | Accelerated SAP implementation | Work during public holidays
* see "Risk register" for more details
Notes: L’idée est de suivre l’évolution des risques tout au long du projet (Criticité, mesures préventives et correctives)

## Slide 10: Project risk review: Risk matrix
* see "Risk register" for more details
Notes: L’idée est de suivre l’évolution des risques tout au long du projet (Criticité, mesures préventives et correctives)

## Slide 11: Evolution of the project KPIs
KPI | Target | Current status | Tendency | Comments
Implementation budget | 515 K euros | Satisfactory (Actual aligned with Planned) | Stable | On track
Annual operating cost | 310 K euros | Satisfactory (Project on schedule) | Improvement | Confidence increases with results
Removal of the 2 units assigned to daily corrections | Reassigned | Satisfactory (Huge corrective work) | Degradation | The cleaning work will go a long way in future efficiency
Commissioning | 6 months | Satisfactory (Project on schedule) | Improvement | The cleaning work will go a long way in future efficiency
Return on investment | 1 year | Satisfactory (Project on schedule) | Improvement | On track
Internal customer satisfaction | 90% | Satisfactory (Project on schedule) | Improvement | Growing confidence in the benefits of the project after joint testing
External customer satisfaction | 100% | Satisfactory (Project on schedule) | Stable | To be measured in the first quarter of 2022

## Slide 12: Decisions to be made / Arbitration to be made
Outstanding issues and decisions to be taken
Decision 1
  When is the perfect time to communicate with our customers about the planned changeover at the end of November and the possible slight disruptions?
Decision 2
  Confirm when we will officially cancel contracts for old systems - to avoid double costs
Décision 3
  Need additional resources for data cleansing

## Slide 13: Change Requests Validation
* see "Change requests register" for more details

## Slide 14: Questions?
The project team will be happy to answer all questions, comments and suggestions

## Slide 15: Next meetings
Next steering committee meetings :
2022-10-29
2022-11-26
2022-12-17