## Classic project macro-planning
Name /Project Code | Project SAP 30 / CMRL | [24 empty] | Creation date | [6 empty] | 2022-01-01
Reference | Program PG01 | Programme PG01/Portfolio PF02 | [23 empty] | Version date | [6 empty] | 2022-01-01
Project manager | Mme.Dupont | Mme.Dupont | [23 empty] | Version N° | [6 empty] | V2.3
Service/Organization | Marketing/ Society XY | Marketing/ Société XY
Phases/Task | Year | 2022 | [41 empty] | 2022
| Month | March | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  |  | January
| Week | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4
Phase 1: Initialization
Project charter approval
Phase 2: Planification
Detailed plan and Specifications
Phase 3: Realization
Development
Prototype and tests
Key user approval
Phase 4: Control and monitoring
Deployment
Go Live
Phase 5: Project closure
Project delivered
Macro planning

## Agile project macro-planning
Name /Project Code | Project SAP 30 / CMRL | [24 empty] | Creation date | [6 empty] | 2022-01-01
Reference | Programme PG01 | Programme PG01/Portfolio PF02 | [23 empty] | Version date | [6 empty] | 2022-01-01
Project manager | Mme.Dupont | Mme.Dupont | [23 empty] | Version N° | [6 empty] | V2.3
Service/Organization | Marketing/ Society XY | Marketing/ Société XY
Phases/Tasks | Years | 2022 | [41 empty] | 2022
| Month | March | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  |  | January
| Week | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4
Phase 1: Needs collection
Creation of the product backlog
Phase 2: Iteration 1
Sprint planning
Developments
Sprint review
Sprint retrospective
Phase 3: Iteration 2
Sprint planning
Developments
Sprint review
Sprint retrospective
Phase n: Iteration n
Sprint planning
Developments
Sprint review
Sprint retrospective
Project delivered
Macro planning

## CMRL project macro-planning
Name /Project Code |  | Project SAP 30 / CMRL | [32 empty] | Creation date | [7 empty] | 2022-01-01
Reference |  | Programme PG01 | Programme PG01/Portfolio PF02 | [31 empty] | Version date | [7 empty] | 2022-01-01
Project manager |  | Mme.Dupont | Mme.Dupont | [31 empty] | Version N° | [7 empty] | V2.3
Service/Organization |  | Marketing/ Society XY | Marketing/ Société XY
Phases/Taches |  | Years | 2022 | [41 empty] | 2022
|  | Month | March | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  |  | January
|  | Week | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4
Phase 1: Initiation
Opportunity study and project approval
Development of the Project Charter
Approval of the charter
Phase 2: Planification
General design
Detailed plan and Specifications
Approval of detailed plan and specifications
Phase 3: Execution
Configuration of CMRL specifics
Tests and confirmation
Key user approval
Phase 4: Control and monitoring
Integration and consolidation tests
Pre-productive environment
Deployment
Tilting and validation
Validation of the productive environment
PV Acknowledgment of Reception
Phase 5: Project closure
List of corrections
Documentation lessons learned
Decommissioning old systems
closeout meeting
Macro planning