## Slide 1
Kick-OFF meeting
SAP 30 / CMRL
27/4/2022

## Slide 2: Agenda
  Project Background
  Expected benefits
  Objectives and KPIs
  The Project Team
  Project stakeholders
  Roles & Responsibilities: RACI
  The Steering Committee
  The project phases
  Macro Planning
  Initial Risks
  Project budget
  Governance
  Next Meetings

## Slide 3: Project Background
Our Regional Assembly Center in Lille must switch to SAP
The costs of CMRL's IT systems are excessively high
Integration with Headquarters systems as well as multiple corrections are extremely manual (2 full-time resources)
The systems are no longer maintained and do not support our expansion plans
The risks of negative control and audit are very high
The Management Committee examined our feasibility study and approved the creation of the SAP 30 / CMRL project under the following conditions:
  Estimated budget of 515,000 euros
  Delivery end of November 2022
  Closure of 2022 books on the new system
  The system must support the CMRL production increase project (CMRL 2022/88)

## Slide 4: Expected benefits
Improve productivity
Reduce maintenance costs
Improve user experience
Improve reliability and data protection
* see "Business Case" for quantified benefits

## Slide 5: Objectives and KPIs
All current functionalities will be replaced by central systems on December 31, 2022
The old systems will be disconnected on January 1, 2023.
The annual closing of the CMRL will be done on the SAP system before January 7, 2023.

## Slide 6: Objectives and KPIs (continued)
KPI | Target
Implementation budget | 515 K euros
Annual operating cost | 310 K euros
Removal of the 2 units assigned to daily corrections | Re-assignments
Commissioning | 6 months
Return On Investment | 1 year
Internal customer satisfaction | 90%
External customer satisfaction | 100%

## Slide 7: Project team
Chantal DUPONT Chef de Projet
SAP EXPERTS Purchases
SAP EXPERTS Finance
Jean ALBERT
SAP Purchasing Coordinator
Monique DAVANT SAP Finance Coordinator
Denise
ATTALI SAP Sales Coordinator
MARIE BERTHELETTE Executive assistant
Eric Duteil SAP Logistics Coordinator
SAP EXPERTS Sales
Olivier ROBESPIERRE
Sponsor
SAP EXPERTS Logistic

## Slide 8: Project stakeholders
Internal services
Purchasing
Marketing/Sales
Logistics
Finance
DSI
External partners
Auditors
Suppliers
SAP
HP

## Slide 9: Roles & Responsibilities : RACI Matrix
* see document "RACI Matrix" for more details

## Slide 10: The Steering Committee
Headquarters
Gilles PUCCINI – CEO
Daniel CHÂTEAU – IT Director
Chantal DUPONT –Project manager
CMRL
Thierry GAVEAU –CMRL Director
Olivier ROBESPIERRE – CMRL Finance Director and Sponsor
Jacques MEUNIER – CMRL Administrative Manager and Integration / Training
To be defined–Change and Communication Manager

## Slide 11: The project phases
MARCH-APRIL
Initialization
Opportunity Study
Project charter
MAY-JUNE
Planning
Detailed Requirements and Detailed Plan
JULY-SEPTEMBER
Realization
Configuration of CMRL specifics, tests and validations
OCTOBER-DECEMBER
Control and monitoring
Consolidation tests
Deployment
Failover / validation
JANUARY 2023
Project Closure
Financial close 2022 on SAP and shutdown of old systems
Project closing meeting

## Slide 12: Macro Planning

## Slide 13: Initial Risks Register
Description | Gravity | Probability | Criticality | Consequence if happen | Preventive actions | Corrective actions
Status-Quo | Catastrophic | Unlikely | Very critical | Costs, deadlines, strategy | Start of the SAP CMRL project | Start of the SAP CMRL project
Control / Audit | Severe | Likely | Very critical | Costs and deadlines | Accelerated SAP implementation | Agreements with auditors
Lack of support or interest | Major | Unlikely | Critical | Deadlines and Quality | Communication plan and assignment of a change manager | Transparent communication
Dependencies between projects | Major | Likely | Critical | Cost, deadlines, strategy | SAP project and CMRL expansion project in the same portfolio | Change management
Deadline December 2022 | Major | Improbable | Moderate | Cost, deadlines, strategy | Accelerated SAP implementation | Work during public holidays
* see "Risk register" for more details

## Slide 14: Initial Risks Analysis: Risk matrix
* see "Risk register" for more details

## Slide 15: Project Budget
Budget BUILD (Set up cost) |  |  |  | Budget RUN (Annual operating cost) | 
Internal HR | RH of service providers | Equipment | Licenses | TMA | Licenses
115K€ | 300K€ | 50K€ | 50K€ | 110K€ | 200K€
Total Build = 515 K€ |  |  |  | Annual Operating Cost= 310 K€ | 

## Slide 16: Project Governance (1/3)
Participants list
Chantal DUPONT
Jacques MEUNIER
Olivier ROBESPIERRE
To be confirmed (Change and communication Manager)
SAP process coordinators
Weekly project committee
Mission: Monitor the project execution, risks, action plan …

## Slide 17: Project Governance (2/3)
Participants list
Chantal DUPONT
Jacques MEUNIER
Denise ATTALI
Monique DAVANT
Eric DUTEIL
Jean ALBERT
SAP experts in IT
Weekly technical committee
Mission: Address technical matters, develop the architecture diagram …

## Slide 18: Project Governance(3/3)
Participants list
Chantal DUPONT
Jacques MEUNIER
Olivier ROBESPIERRE
To be confirmed (Change and Communication Manager)
SAP process coordinators
Gilles PUCCINI (Chief Executive Officer Confassis)
Thierry GAVEAU ( CMRL Director)
Daniel CHÂTEAU ( IT Director)
Steering committee
Mission: Monitor the overall progress of the project, arbitrate change requests, make strategic decisions

## Slide 19: Questions
  Each question helps us to improve
  Your next question may help us to prevent unnecessary mistakes
  Open and transparent communication is essential for the success of projects

## Slide 20: Next meetings
Here are the dates of the next meetings
First project committee, Friday, May 7, 2022 at 9:00 a.m.
Will take place every Friday at the same time
First technical committee, Monday, May 10, 2022 at 3:00 p.m.
Will take place every Monday at the same time
First steering committee, Friday May 28, 2022 at 11:00 a.m.
Will take place every last Friday of the month at the same time
The next Management Board meeting will take place on 29 June 2022
The Management Board will meet at each major milestone
The management Board will then give its opinion on the continuation of the project.

## Slide 21: Additional topics proposed
  The main documentation of the projects (Contract, Spec, SLA, PAQ, PMP etc.)
  The project set-up and rules: the way the team exchanges (email / instant messaging)
  the reporting methods, etc…