## Slide 1
Project committee meeting
SAP30/CMRL
On 2022-09-28

## Slide 2: Agenda
  Progress by module
  Project performance monitoring
    Budget review
    Schedule review
  Risk review
  Action plan
  Questions
  Next Meetings

## Slide 3: Progress monitoring: Finance
Workshops or meetings to organize
  Review the Finance test results
  Finalize the list of corrections and share it with experts Review and update the issues and risks register
To be done
  Before integration tests:
    Review the scenarios and complete the examples
    Distribute tests by area of expertise
    Finalize training materials
  After the integration tests:
    Adapt the consolidation test plan
    Confirm the training plan and send the invitations
    Complete the tests to adapt them to the pre-production environment
Done
  FI / CO configuration and unit tests
  Parameterization and unit tests Fixed assets
  Corrections of encountered problems
  Data set for validation of fixed asset calculations
  Validation by key users
  Accounts cleaning
  Chart of Accounts agreement

## Slide 4: Progress monitoring: Sales
Workshop or meeting to organize
  Review of sales test results Finalize the list of corrections and communicate to the experts Review and update of the problem and risk register Meeting with CRM experts to establish the implementation plan
To be done
  Before integration tests
    Review the scenarios and complete the examples Distribute tests by area of expertise Finalize training materials
  After integration tests
    Adapt the consolidation test plan Confirm the training plan and send the invitations Complete the tests to adapt them to the pre-production environment
Done
  SD configuration and unit tests
  Corrections
  Key users validation
  Cleansing the customer file
  Customer hierarchy agreement
  Rebates and discounts agreement
  Collection of CRM requirements

## Slide 5: Progress monitoring: Purchasing
Workshops or meetings to organize
  Review of Purchasing test results Finalize the list of corrections and communicate to the experts Review and update of the problem and risk register Meeting with Ariba experts
To be done
  Before integration tests
    Review the scenarios and complete the examples Distribute tests by area of expertise Finalize training materials
  After integration tests
    Adapt the consolidation test plan Confirm the training plan and send the invitations Complete the tests to adapt them to the pre-production environment
Done
  Configuration and unit tests
  Corrections
  Validation by key users
  Cleansing accounts payable
  Expense management agreement
  Agreement payment rules
  Collection of "auction" requirements

## Slide 6: Progress monitoring: Logistics
Workshops or meetings to organize
  Review of logistics test results Finalize the list of corrections and communicate to the experts Review and update of the problem and risk register Meeting with interface experts
Before integration tests
  Before integration tests
    Review the scenarios and complete the examples Distribute tests by area of expertise Finalize training materials
  After integration tests
    Adapt the consolidation test plan Confirm the training plan and send the invitations Complete the tests to adapt them to the pre-production environment
Done
  MM setup and unit tests
  Corrections
  Validation by key users
  Cleansing the product file
  Transport management agreement
  Storage rules agreement
  Collection of interfaces requirements

## Slide 7: Progress monitoring: Production
Workshops or meetings to organize
  Review of production test results
  Finalize the list of corrections and communicate to the experts
  Review and update of the problem and risk register
  Meeting with interface experts
To be done
  Before integration tests
    Review the scenarios and complete the examples
    Distribute tests by area of expertise
    Finalize training materials
  After integration tests:
    Adapt the consolidation test plan
    Confirm the training plan and send the invitations
    Complete the tests to adapt them to the pre-production environment
Done
  Configuration and unit tests
  Corrections
  Validation by key users
  Collection of interfaces requirements

## Slide 8: Progress monitoring: Master Data
Workshops or meetings to organize
  Review of correction and loading rules with CMRL experts
  Finalize the list of corrections and communicate to the experts
  Review and update of the issues and risks register
  Selection of part-time resources to manage the volume of information
To be done
  Before integration tests
    Complete corrections
    Complete datasets for testing
    Coordination with other work area
  After integration tests
    Adapt consolidation datasets
    Develop procedures for switching, correcting and loading data
    User-validator selection
Done
  File cleansing
  Fix issues (in progress)
  Definition of needs during integration and consolidation tests
  Preparation of test data sets

## Slide 9: Project performance: Budget review
Chart: Budget SAP30/CMRL End of September 2022
| Total | Réel | Planifié à cette date
sept-21 | 420000 | 182500 | 184000
Notes: Possible de détailler la performance par services/périmètres. Par exemple splitter cet indicateur entre finances/logistique/achats etc.

## Slide 10: Project performance: Earned value analysis ½ *
See "Budget monitoring report" for more details

## Slide 11: Project performance: Earned value analysis 2/2 *
Chart: Valeur Acquise SAP30/CMRL
| 44256 | 44287 | 44317 | 44348 | 44378 | 44409 | 44440 | 44470 | 44501 | 44531 | 44562 | 44593
Valeur Planifiée (VP) | 5000 | 22000 | 39000 | 56000 | 94000 | 132000 | 170000 | 181500 | 252000 | 321000 | 344000 | 346000
Valeur Acquise (VA) | 3000 | 18880 | 35760 | 53000 | 93660 | 131320 | 170000 | 181500 | 248800 | 333000 | 344000 | 346000
Coût Réel (CR) | 4000 | 22000 | 39000 | 55500 | 93500 | 131500 | 169500 | 181000 | 261000 | 335000 | 355000 | 357000
See "Budget monitoring report" for more details

## Slide 12: Performance de projet : Revue du Planning
Project performance: Schedule review
The movements of the past period :
  Delivery of parameterized and tested systems in all areas of work
  Data cleaning and corrections
  Collection of interface requirements
  Collection of CRM requirements
  Validation by key users
  Planned for the following period:
  Integration test
  Consolidation test
  Finalized training materials
  Detailed data failover plan
  Detailed acceptance test plan for solutions in all areas of work
  Preparation of the functional and operational changeover plan
Notes: Possible de garder en référence la Baseline.
Et donc afficher le planning original et le planning réel, pour mettre en évidence les glissement de planning (en retard comme en avance d’ailleurs)

## Slide 13: Project risks review
Description | severity | Probability | Criticality | Consequence if happen | Preventive Actions | Corrective Actions
Status-Quo | Catastrophic | Unlikely | Very critical | Cost, deadline, strategy | Start of the SAP CMRL project | Start of the SAP CMRL project
Control/Audit | Severe | Likely | Very critical | Cost and deadlines | Accelerated SAP implementation | Agreements with auditors
Lack of support or interest | Major | Unlikely | Critical | Deadlines and quality | Communication plan and assignment of a change manager | Transparent communication
Dependencies between projects | Major | Likely | Critical | Cost, deadline, strategy | SAP project and CMRL expansion project in the same portfolio | Change management
Deadline December 2022 | Major | Improbable | Moderated | Cost, deadline, strategy | Accelerated SAP implementation | Work during public holidays
* see "Risk register" for more details
Notes: L’idée est de suivre l’évolution des risques tout au long du projet (Criticité, mesures préventives et correctives)

## Slide 14: Project risk review: Risk matrix
* see "Risk register" for more details
Notes: L’idée est de suivre l’évolution des risques tout au long du projet (Criticité, mesures préventives et correctives)

## Slide 15: Action register
* see "Action register” for more details

## Slide 16: Questions
  Do you have any questions for the group?
  Do you have questions or actions to communicate to the steering committee?
  Updates or corrections?
  Updates to the issues and risk register?

## Slide 17: Next meetings
Next project committee meetings:
  2022-10-01
  2022-10-08
  2022-10-15

## Slide 18: Addition proposals:
Members present and excused
Follow-up of deliverables if necessary (see deliverables register)