## User guide
Using the testing plan template
I. How to use the template
1. Go to the "Integration testing" sheet
Fill in the following columns:
Project deliverables: | Start by listing all the deliverables for your project. Refer to the deliverables tracking document.
Theme: | Group the deliverables by theme according to your nomenclature (lists and reports, fixed assets, general, or other)
Scenario: | Describe the different test scenarios for each deliverable
Expected result: | For each scenario, correspond the expected results of their execution. Describe the expected outcome for each scenario.
CORRECT: | Mark (x) the cells in front of the expected results that you think are correct.
FALSE: | Mark (x) the cells in front of the expected results that you judge to be false.
IN PROGRESS: | When a test is started but not completed, it is noted as "in progress". Mark (x) the current items.
WAITING: | When a test is being processed, it is marked as "pending". Mark (x) the pending items.
Not applicable: | Some tests may not be relevant for this particular testing period. They will therefore be noted as “not applicable”. Mark these items.
Error: | If there is an error, the error code and description should be noted and, after correction, the test will be repeated until it is correct.
Correction: | Note the corrections made
Dated: | Put the correction date
TOTALS | The "Correct", "False", "In progress", "Still to be done", "Not applicable" cells display the sum of the elements checked for all the scenarios. The calculation is done automatically. The rate of progress automatically takes into account the sum of the correct, false, outstanding, and not applicable values, by dividing it by the total sum of all the scenarios.
2. Go to the "Consolidation testing" sheet
Repeat exactly the same process described for the operation of the "integration tests" sheet
Adding a row (line)
To add a row, just insert a new row at the bottom of the table above the last row.

## Integration testing
Name /Project Code | SAP30/CMRL | [7 empty] | Creation date |  | 2022-10-15
Reference | Strategy2022/CMRL | Programme PG01/Portfolio PF02 | [6 empty] | Version date |  | 2022-10-17
Project manager | Chantal Dupont | Mme.Dupont | [6 empty] | Version N° |  | V2.0
Service/Organization | Confassis S.A. | Marketing/ Société XY
| Totals | 176 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0%
|  | TOTAL |  | CORRECT | FALSE | IN PROGRESS | WAITING | NOT APPLICAL |  |  | RATE
[7 empty] | A FAIRE |  |  |  | OF PROGRESS
|  |  |  | 0% | 0% | 0% | 0% | 0%
| Project deliverables | Theme | Scenario | Expected result | CORRECT | FALSE | IN PROGRESS | WAITING | NOT APPLICAL | Error | Correction | Date
| FINANCES | General | Inter-company invoicing
Closure
New year preparation
Reconciliation of accounts
SOX Reports
Financial reports
Inter-company transfers
Bank accounting
Liquidity management
Bank communications management
Sale of receivables
Expense
Credit check
Cash advances
Management reports
Service costs
Inter-company costs
Preparation of forecasts
Bank management
Tax returns registration
VAT return
Intrastat / Extrastat declaration
Manual ledger entry
Inter-company financial processes
Incoming payment
Outgoing payment
Input-output log
Debt collection
Complaints management
Central bank reports
Credit check
Credit check - static and dynamic
Blocked orders and inquiries
Credit: release orders
Credit: cancel orders
FI / CO invoice registration
FI product movements
|  | Fixed assets | Enter immobilization movement
Change asset document
Display asset document.
Cancel individual immob
Unplanned depreciation
Immob output. per sale with customer
Deriv. autom. character : access
Immob output. per sale with customer
Last exit on immob complex.
Immob output. per sale without customer
Immob output. by scrapping
Immob output. by disposal
Accounting revaluation
Revaluation
Writing correction on domains
Post document
Post document in grp. ledgers
Credit note in exercise following invoice
Enter credit memo in invoice exercise
Investment encouragement
Manual damping
Transf. Manual prov. p. real estate renewal.
Asset transfer cancellation via part number
Invest. Additional
Additional investment
Enter invest. additional
Subsequent product
Subsequent costs
Other movement
Other movement
FI-AA reconciliation analysis
FI-AA reconciliation analysis
Transfer of immob inter-company
Inter-company transfer
Transfer between tables
| Sales | General | Standard sales
Organizational units
Master data
Order taking
Determination of business partners
Service level agreements
Distribution strategies
Determination of product codes
Substitute products
Reference documents
Availability check and order planning
Customer reservations
Determination of prices and conditions
International order information outside the EU
International order information in EU
Determination of documentation printing
Vendor determination
Determination of the reason for the order
Rejection code determination
Credit check
Billing
Reports
Export
Delivery forecast
Order planning agreements
Correction of planned orders
Cash payment
Credit cards payment
Sales to staff
Returns
Credit notes
Debit Notes
Various credit
Various flow
Consignments
Warranty complaints
Delay management
Customer reservations
Archiving
Cash sales
Return cash sales
Sales campaigns
Special customer requests
Complaints management
Very large orders
B2B portal
CRM Portal
| PURCHASES | General | Sources of supply
Stock inventory of approved suppliers
Consignment stock
Purchases with contracts
Purchases without contracts
Subcontractors
Purchases via subcontractors
Raw materials
Inter-company raw materials
Inter-company semis-finished
Stocks without source
Stock with source
Uncoded parts
Purchases for Sales, Marketing or HR
Service monitoring process
Purchases on catalogs with receipt
Inventory management
Reports
Analyzes
| LOGISTIC | Lists and Reports | Replenishment of sister companies
Storage
Sub-contractors with transport
Sub-contractors without transport
External mounting
Physical inventory
Internal filing process
Intrastat / Extrastat movements
|  | Supply Chain | Inter-company replenishment
Third-party stock management
Production planning
Product allocations
Transport planning
Interfaces
Imports
| PRODUCTION | Planification | Factory maintenance
Product needs planning
Production planning
Detailed planning
Production execution
Product specifications
Special order production
Equipment settings
Factory project monitoring
Semi-finished products
|  | Execution | Storage
Constructions
Assembly
Preparation
Kanban
Inventories
| REPPORTS | Finances | Financial Reports
|  | Sales | Sales Reports
|  | Logistic | Logistics Reports
|  | Production | Production report
|  | Purchases | Purchasing Reports
|  | Services | Services Reports
|  | Diverse | Configurable reports
Testing plan - Integration

## Consolidation testing
Name /Project Code | SAP30/CMRL | [7 empty] | Creation date |  | 2022-10-15
Reference | Strategy2022/CMRL | Programme PG01/Portfolio PF02 | [6 empty] | Version date |  | 2022-10-17
Project manager | Chantal Dupont | Mme.Dupont | [6 empty] | Version N° |  | V2.0
Service/Organization | Confassis S.A. | Marketing/ Société XY
| TOTAUX | 176 |  | 0 | 0 | 0 | 176 | 0 |  |  | 0%
|  | TOTAL |  | CORRECT | FALSE | In progress | WAITING | NOT APPLICAL |  |  | Ratio
[7 empty] | A FAIRE |  |  |  | Of progress
|  |  |  | 0% | 0% | 0% | 100% | 0%
| Project deliverables | Theme | Scenario | Expected result | CORRECT | FALSE | In progress | WAITING | NOT APPLICAL | Error | Correction | Date
| FINANCES | General | Inter-company invoicing |  |  |  |  | X
|  |  | Closure |  |  |  |  | X
|  |  | New year preparation |  |  |  |  | X
|  |  | Reconciliation of accounts |  |  |  |  | X
|  |  | SOX Reports |  |  |  |  | X
|  |  | Financial reports |  |  |  |  | X
|  |  | Inter-company transfers |  |  |  |  | X
|  |  | Bank accounting |  |  |  |  | X
|  |  | Liquidity management |  |  |  |  | X
|  |  | Bank communications management |  |  |  |  | X
|  |  | Sale of receivables |  |  |  |  | X
|  |  | Expense |  |  |  |  | X
|  |  | Credit check |  |  |  |  | X
|  |  | Cash advances |  |  |  |  | X
|  |  | Management reports |  |  |  |  | X
|  |  | Service costs |  |  |  |  | X
|  |  | Inter-company costs |  |  |  |  | X
|  |  | Preparation of forecasts |  |  |  |  | X
|  |  | Bank management |  |  |  |  | X
|  |  | Tax returns registration |  |  |  |  | X
|  |  | VAT return |  |  |  |  | X
|  |  | Intrastat / Extrastat declaration |  |  |  |  | X
|  |  | Manual ledger entry |  |  |  |  | X
|  |  | Inter-company financial processes |  |  |  |  | X
|  |  | Incoming payment |  |  |  |  | X
|  |  | Outgoing payment |  |  |  |  | X
|  |  | Input-output log |  |  |  |  | X
|  |  | Debt collection |  |  |  |  | X
|  |  | Complaints management |  |  |  |  | X
|  |  | Central bank reports |  |  |  |  | X
|  |  | Credit check |  |  |  |  | X
|  |  | Credit check - static and dynamic |  |  |  |  | X
|  |  | Blocked orders and inquiries |  |  |  |  | X
|  |  | Credit: release orders |  |  |  |  | X
|  |  | Credit: cancel orders |  |  |  |  | X
|  |  | FI / CO invoice registration |  |  |  |  | X
|  |  | FI product movements |  |  |  |  | X
|  | Fixed assets | Enter immobilization movement |  |  |  |  | X
|  |  | Change asset document |  |  |  |  | X
|  |  | Display asset document. |  |  |  |  | X
|  |  | Cancel individual immob. |  |  |  |  | X
|  |  | Unplanned depreciation |  |  |  |  | X
|  |  | Immob output. per sale with customer |  |  |  |  | X
|  |  | Deriv. autom. character : access |  |  |  |  | X
|  |  | Immob output. per sale with customer |  |  |  |  | X
|  |  | Last exit on immob complex. |  |  |  |  | X
|  |  | Immob output. per sale without customer |  |  |  |  | X
|  |  | Immob output. by scrapping |  |  |  |  | X
|  |  | Immob output. by disposal |  |  |  |  | X
|  |  | Accounting revaluation |  |  |  |  | X
|  |  | Revaluation |  |  |  |  | X
|  |  | Writing correction on domains |  |  |  |  | X
|  |  | Post document |  |  |  |  | X
|  |  | Post document in grp. ledgers |  |  |  |  | X
|  |  | Credit note in exercise following invoice |  |  |  |  | X
|  |  | Enter credit memo in invoice exercise |  |  |  |  | X
|  |  | Investment encouragement |  |  |  |  | X
|  |  | Manual damping |  |  |  |  | X
|  |  | Transf. Manual prov. p. real estate renewal. |  |  |  |  | X
|  |  | Asset transfer cancellation via part number |  |  |  |  | X
|  |  | Invest. Additional |  |  |  |  | X
|  |  | Additional investment |  |  |  |  | X
|  |  | Enter invest. additional |  |  |  |  | X
|  |  | Subsequent product |  |  |  |  | X
|  |  | Subsequent costs |  |  |  |  | X
|  |  | Other movement |  |  |  |  | X
|  |  | Other movement |  |  |  |  | X
|  |  | FI-AA reconciliation analysis |  |  |  |  | X
|  |  | FI-AA reconciliation analysis |  |  |  |  | X
|  |  | Transfer of immob. inter-company |  |  |  |  | X
|  |  | Inter-company transfer |  |  |  |  | X
|  |  | Transfer between tables |  |  |  |  | X
| Sales | General | Standard sales |  |  |  |  | X
|  |  | Organizational units |  |  |  |  | X
|  |  | Master data |  |  |  |  | X
|  |  | Order taking |  |  |  |  | X
|  |  | Determination of business partners |  |  |  |  | X
|  |  | Service level agreements |  |  |  |  | X
|  |  | Distribution strategies |  |  |  |  | X
|  |  | Determination of product codes |  |  |  |  | X
|  |  | Substitute products |  |  |  |  | X
|  |  | Reference documents |  |  |  |  | X
|  |  | Availability check and order planning |  |  |  |  | X
|  |  | Customer reservations |  |  |  |  | X
|  |  | Determination of prices and conditions |  |  |  |  | X
|  |  | International order information outside the EU |  |  |  |  | X
|  |  | International order information in EU |  |  |  |  | X
|  |  | Determination of documentation printing |  |  |  |  | X
|  |  | Vendor determination |  |  |  |  | X
|  |  | Determination of the reason for the order |  |  |  |  | X
|  |  | Rejection code determination |  |  |  |  | X
|  |  | Credit check |  |  |  |  | X
|  |  | Billing |  |  |  |  | X
|  |  | Reports |  |  |  |  | X
|  |  | Export |  |  |  |  | X
|  |  | Delivery forecast |  |  |  |  | X
|  |  | Order planning agreements |  |  |  |  | X
|  |  | Correction of planned orders |  |  |  |  | X
|  |  | Cash payment |  |  |  |  | X
|  |  | Credit cards payment |  |  |  |  | X
|  |  | Sales to staff |  |  |  |  | X
|  |  | Returns |  |  |  |  | X
|  |  | Credit notes |  |  |  |  | X
|  |  | Debit Notes |  |  |  |  | X
|  |  | Various credit |  |  |  |  | X
|  |  | Various flow |  |  |  |  | X
|  |  | Consignments |  |  |  |  | X
|  |  | Warranty complaints |  |  |  |  | X
|  |  | Delay management |  |  |  |  | X
|  |  | Customer reservations |  |  |  |  | X
|  |  | Archiving |  |  |  |  | X
|  |  | Cash sales |  |  |  |  | X
|  |  | Return cash sales |  |  |  |  | X
|  |  | Sales campaigns |  |  |  |  | X
|  |  | Special customer requests |  |  |  |  | X
|  |  | Complaints management |  |  |  |  | X
|  |  | Very large orders |  |  |  |  | X
|  |  | B2B portal |  |  |  |  | X
|  |  | CRM Portal |  |  |  |  | X
| PURCHASES | General | Sources of supply |  |  |  |  | X
|  |  | Stock inventory of approved suppliers |  |  |  |  | X
|  |  | Consignment stock |  |  |  |  | X
|  |  | Purchases with contracts |  |  |  |  | X
|  |  | Purchases without contracts |  |  |  |  | X
|  |  | Subcontractors |  |  |  |  | X
|  |  | Purchases via subcontractors |  |  |  |  | X
|  |  | Raw materials |  |  |  |  | X
|  |  | Inter-company raw materials |  |  |  |  | X
|  |  | Inter-company semis-finished |  |  |  |  | X
|  |  | Stocks without source |  |  |  |  | X
|  |  | Stock with source |  |  |  |  | X
|  |  | Uncoded parts |  |  |  |  | X
|  |  | Purchases for Sales, Marketing or HR |  |  |  |  | X
|  |  | Service monitoring process |  |  |  |  | X
|  |  | Purchases on catalogs with receipt |  |  |  |  | X
|  |  | Inventory management |  |  |  |  | X
|  |  | Reports |  |  |  |  | X
|  |  | Analyzes |  |  |  |  | X
| LOGISTIC | Lists and Reports | Replenishment of sister companies |  |  |  |  | X
|  |  | Storage |  |  |  |  | X
|  |  | Sub-contractors with transport |  |  |  |  | X
|  |  | Sub-contractors without transport |  |  |  |  | X
|  |  | External mounting |  |  |  |  | X
|  |  | Physical inventory |  |  |  |  | X
|  |  | Internal filing process |  |  |  |  | X
|  |  | Intrastat / Extrastat movements |  |  |  |  | X
|  | Supply Chain | Inter-company replenishment |  |  |  |  | X
|  |  | Third-party stock management |  |  |  |  | X
|  |  | Production planning |  |  |  |  | X
|  |  | Product allocations |  |  |  |  | X
|  |  | Transport planning |  |  |  |  | X
|  |  | Interfaces |  |  |  |  | X
|  |  | Imports |  |  |  |  | X
| PRODUCTION | Planification | Factory maintenance |  |  |  |  | X
|  |  | Product needs planning |  |  |  |  | X
|  |  | Production planning |  |  |  |  | X
|  |  | Detailed planning |  |  |  |  | X
|  |  | Production execution |  |  |  |  | X
|  |  | Product specifications |  |  |  |  | X
|  |  | Special order production |  |  |  |  | X
|  |  | Equipment settings |  |  |  |  | X
|  |  | Factory project monitoring |  |  |  |  | X
|  |  | Semi-finished products |  |  |  |  | X
|  | Execution | Storage |  |  |  |  | X
|  |  | Constructions |  |  |  |  | X
|  |  | Assembly |  |  |  |  | X
|  |  | Preparation |  |  |  |  | X
|  |  | Kanban |  |  |  |  | X
|  |  | Inventories |  |  |  |  | X
| REPPORTS | Finances | Financial Reports |  |  |  |  | X
|  | Sales | Sales Reports |  |  |  |  | X
|  | Logistic | Logistics Reports |  |  |  |  | X
|  | Production | Production report |  |  |  |  | X
|  | Purchases | Purchasing Reports |  |  |  |  | X
|  | Services | Services Reports |  |  |  |  | X
|  | Diverse | Configurable reports |  |  |  |  | X
Testing plan - Consolidation