## User manual
Using the project budget monitoring template
Prerequisites before entering data
In order to control the project performance, you must monitor the scope execution progress, the costs consumed and the schedule. Thus, you'll start filling in the list of project tasks, referring to your project schedule.
To monitor the budget and the schedule, you need to get a grasp of the following concepts:
Actual Cost (AC): | Cost actually consumed for the performed work
Planned Value (PV): | Budgeted cost of planned work
Earned Value (EV): | Budgeted cost of performed work (The cost we were willing to pay for work done to date)
Cost Performance Index (CPI): | Earned value (EV) / Actual cost (AC)
Schedule Performance Index (SPI): | Earned value (EV) / Planned value (PV)
BAC (Budget at Completion) | Budget expected at project completion for each task
1. Go to the "PV" sheet
Fill in the planned value (budgeted cost of scheduled work), for each task, for each month.
The BAC (budget at completion) is the sum of the monthly budgets provided for each task. It is calculated automatically from the data entered
2. Go to the "AC" sheet
Enter the cost actually consumed for each task and for each month.
The actual Cost of the Project to date is calculated automatically
3. Go to the "EV" sheet
Fill in the completion rate for each task per month. Earned value is calculated automatically by multiplying the percentage of completion by the planned budget
4. Go to the "Budget Monitoring" sheet
Here you have a summary of the cumulative values of the project: PV, AC and EV. The analysis of the earned value is illustrated by the graph.
Performance metrics are then calculated automatically
← You can change the labels for the periods (e.g. Week 1/2/3, Jan / Feb / Mar, etc.)
← Enter or edit the values in the white cells.
← To add other tasks, insert lines above this one.
Actual Cost and Earned Value
The cumulative actual cost (AC) and the cumulative earned value (EV) are automatically copied from the "AC" and "EV" sheets and are used to calculate the differences
Project performance metrics
The Cost Variance (CV), Schedule Variance (SV), Cost Performance Indicators (CPI) and Schedule Performance Indicators (SPI) are calculated automatically.
Data graph
The graph for AC, PV and EV is drawn up automatically

## PV
Planned Value Worksheet
This sheet is used to fill in the planned value (PV)
The budget of the planned work, for each task, each month.
WBS | Task name | Planned budget for the task | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01
1 | Expression of needs | 20000 | 2021-03-01: 5000; 2021-04-01: 5000; 2021-05-01: 5000; 2021-06-01: 5000
2 | Planning | 36000 | 2021-04-01: 12000; 2021-05-01: 12000; 2021-06-01: 12000
3 | Financial settings and tests | 24000 | 2021-07-01: 8000; 2021-08-01: 8000; 2021-09-01: 8000
4 | Configuration and tests Sales | 24000 | 2021-07-01: 8000; 2021-08-01: 8000; 2021-09-01: 8000
5 | Purchasing configuration and tests | 24000 | 2021-07-01: 8000; 2021-08-01: 8000; 2021-09-01: 8000
6 | Logistics configuration and testing | 24000 | 2021-07-01: 8000; 2021-08-01: 8000; 2021-09-01: 8000
7 | Configuration and production tests | 6000 | 2021-07-01: 2000; 2021-08-01: 2000; 2021-09-01: 2000
8 | Master Data preparation | 16000 | 2021-07-01: 4000; 2021-08-01: 4000; 2021-09-01: 4000; 2021-10-01: 4000
9 | User training | 7500 | 2021-10-01: 7500
10 | Operational switchover | 54500 | 2021-11-01: 54500
11 | User support | 45000 | 2021-12-01: 45000
12 | Closing November 2021 | 16000 | 2021-11-01: 16000
13 | Operational support | 24000 | 2021-12-01: 12000; 2022-01-01: 12000
14 | Closing December 2021 | 12000 | 2021-12-01: 12000
15 | Documenting lessons learned | 8000 | 2022-01-01: 8000
16 | Project closure | 5000 | 2022-01-01: 3000; 2022-02-01: 2000
- | -
Insert new lines above
| Budget planned at project completion (BAC) | 346000 | 5000 | 17000 | 17000 | 17000 | 38000 | 38000 | 38000 | 11500 | 70500 | 69000 | 23000 | 2000
|  | Cumulative PV | 5000 | 22000 | 39000 | 56000 | 94000 | 132000 | 170000 | 181500 | 252000 | 321000 | 344000 | 346000
Note on A9: Work Breakdown Structure (WBS)
Note on C9: Estimated budget after task completion

## EV
Earned value calculation sheet
This sheet is used to calculate the Earned Value (EV) to date, it is the budgeted cost of the work actually done to date.
Fill in the % of completion of each task to date in order to calculate the Cumulative Earned Value
The Earned Value is calculated automatically by multiplying the% of completion by the planned budget
Cumulative Earned Value (EV)
WBS | Task name | Planned budget for the task | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | % achievement
1 | Expression of needs | 20000 | 2021-03-01: 15%; 2021-04-01: 20%; 2021-05-01: 25%; 2021-06-01: 25%; 2021-07-01: 15% | 100%
2 | Planning | 36000 | 2021-04-01: 33%; 2021-05-01: 33%; 2021-06-01: 34% | 100%
3 | Financial settings and tests | 24000 | 2021-07-01: 33%; 2021-08-01: 33%; 2021-09-01: 34% | 100%
4 | Configuration and tests Sales | 24000 | 2021-07-01: 33%; 2021-08-01: 33%; 2021-09-01: 34% | 100%
5 | Purchasing configuration and tests | 24000 | 2021-07-01: 33%; 2021-08-01: 33%; 2021-09-01: 34% | 100%
6 | Logistics configuration and testing | 24000 | 2021-07-01: 33%; 2021-08-01: 33%; 2021-09-01: 34% | 100%
7 | Configuration and production tests | 6000 | 2021-07-01: 33%; 2021-08-01: 33%; 2021-09-01: 34% | 100%
8 | Master Data preparation | 16000 | 2021-07-01: 25%; 2021-08-01: 25%; 2021-09-01: 25%; 2021-10-01: 25% | 100%
9 | User training | 7500 | 2021-10-01: 100% | 100%
10 | Operational switchover | 54500 | 2021-11-01: 100% | 100%
11 | User support | 45000 | 2021-12-01: 100% | 100%
12 | Closing November 2021 | 16000 | 2021-11-01: 80%; 2021-12-01: 20% | 100%
13 | Operational support | 24000 | 2021-12-01: 100% | 100%
14 | Closing December 2021 | 12000 | 2021-12-01: 100% | 100%
15 | Documenting lessons learned | 8000 | 2022-01-01: 100% | 100%
16 | Project closure | 5000 | 2022-01-01: 60%; 2022-02-01: 40% | 100%
Insert new lines above
|  | Project Earned Value per month | 3000 | 15880 | 16880 | 17240 | 40660 | 37660 | 38680 | 11500 | 67300 | 84200 | 11000 | 2000 | 346000
|  | Cumulative Earned Value (CEV) | 3000 | 18880 | 35760 | 53000 | 93660 | 131320 | 170000 | 181500 | 248800 | 333000 | 344000 | 346000
Note on A12: Work Breakdown Structure (WBS)
Note on C12: Estimated budget after task completion

## AC
Actual Cost Worksheet
This sheet is used to enter the Actual Cost incurred (AC) of each task, also called the Actual Cost of the work performed (ACWP).
Fill in the actual cost of each task, for each month.
Actual Cost of Work Performed
WBS | Task name | Actual cost per task to date | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01
1 | Expression of needs | 19500 | 2021-03-01: 4000; 2021-04-01: 6000; 2021-05-01: 5000; 2021-06-01: 4500
2 | Planning | 36000 | 2021-04-01: 12000; 2021-05-01: 12000; 2021-06-01: 12000
3 | Financial settings and tests | 24000 | 2021-07-01: 8000; 2021-08-01: 8000; 2021-09-01: 8000
4 | Configuration and tests Sales | 24000 | 2021-07-01: 8000; 2021-08-01: 8000; 2021-09-01: 8000
5 | Purchasing configuration and tests | 24000 | 2021-07-01: 8000; 2021-08-01: 8000; 2021-09-01: 8000
6 | Logistics configuration and testing | 24000 | 2021-07-01: 8000; 2021-08-01: 8000; 2021-09-01: 8000
7 | Configuration and production tests | 6000 | 2021-07-01: 2000; 2021-08-01: 2000; 2021-09-01: 2000
8 | Master Data preparation | 16000 | 2021-07-01: 4000; 2021-08-01: 4000; 2021-09-01: 4000; 2021-10-01: 4000
9 | User training | 7500 | 2021-10-01: 7500
10 | Operational switchover | 55000 | 2021-11-01: 55000
11 | User support | 45000 | 2021-12-01: 45000
12 | Closing November 2021 | 17000 | 2021-11-01: 12000; 2021-12-01: 5000
13 | Operational support | 37000 | 2021-11-01: 13000; 2021-12-01: 12000; 2022-01-01: 12000
14 | Closing December 2021 | 12000 | 2021-12-01: 12000
15 | Documenting lessons learned | 5000 | 2022-01-01: 5000
16 | Project closure | 5000 | 2022-01-01: 3000; 2022-02-01: 2000
Insert new lines above
| Actual Project Cost per month |  | 4000 | 18000 | 17000 | 16500 | 38000 | 38000 | 38000 | 11500 | 80000 | 74000 | 20000 | 2000
| Cumulated Actual Project Cost (AC) |  | 4000 | 22000 | 39000 | 55500 | 93500 | 131500 | 169500 | 181000 | 261000 | 335000 | 355000 | 357000
Note on A10: Work Breakdown Structure (WBS)

## Budget monitoring - EV report
|  |  | Earned value analysis report | [5 empty] | EV = Earned Value or Budgeted cost of work performed
[Project name] | [8 empty] | PV = Planned Value or Budgeted cost of planned work
AC = Cost actually consumed for the work performed
| Prepared by: | Chantal DUPONT
| Date: | 2022-02-04
[42]
| For the period: | 2022-01-01
Observations:
This table represents the final result of the SAP30 / CMRL project. The project benefited from the experience of previous SAP projects and the estimates were found to be accurate in terms of cost and earned value. A slight increase in the needs for corrections in Master Data was estimated by the concerned departments, but it didn't influence the budget. This is why the curves are consistent between the Planned and the Actual.
|  |  | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01
Summary of AC, PV, EV and BAC values
|  | Cumulative actual cost (ACC) | 4000 | 22000 | 39000 | 55500 | 93500 | 131500 | 169500 | 181000 | 261000 | 335000 | 355000 | 357000
|  | Cumulative earned value (CEV) | 3000 | 18880 | 35760 | 53000 | 93660 | 131320 | 170000 | 181500 | 248800 | 333000 | 344000 | 346000
|  | Cumulative Planned Value (CPV) | 5000 | 22000 | 39000 | 56000 | 94000 | 132000 | 170000 | 181500 | 252000 | 321000 | 344000 | 346000
|  | Budget at completion (BAC) | 2021-03-01: 346000
Project performance metrics
|  | Cost Variance (CV = EV - AC) | -1000 | -3120 | -3240 | -2500 | 160 | -180 | 500 | 500 | -12200 | -2000 | -11000 | -11000
|  | Schedule Variance (SV = EV - PV) | -2000 | -3120 | -3240 | -3000 | -340 | -680 | 0 | 0 | -3200 | 12000 | 0 | 0
|  | Cost Performance Indicator (IPC = EV / AC) | 0.75 | 0.85818 | 0.91692 | 0.95495 | 1.0017 | 0.99863 | 1.0029 | 1.0028 | 0.95326 | 0.99403 | 0.96901 | 0.96919
|  | Schedule Performance Indicator (SPI = EV / PV) | 0.6 | 0.85818 | 0.91692 | 0.94643 | 0.99638 | 0.99485 | 1 | 1 | 0.9873 | 1.0374 | 1 | 1
|  | Estimated Final Cost (EFC) = BAC / IPC | 461333.3333 | 403177.9661 | 377348.9933 | 362320.7547 | 345408.9259 | 346474.2613 | 344982.3529 | 345046.832 | 362966.2379 | 348078.0781 | 357063.9535 | 357000
If IPC <1, then the budget is over-consumed
If IPC > 1, then the budget is under-consumed

## Project Progress Report
PROGRESS REPORT (1/2)
1. General Information
Project name: |  |  | SAP implementation at the Lille Regional Assembly Center | [6 empty] | Report N°: |  |  | 11
Project manager : |  |  | Chantal Dupont | [6 empty] | Project code: |  |  | SAP30/CMRL
Period covered by the report: |  |  | March 2021 to January 2022 | [6 empty] | Report Date: |  |  | 2022-02-04
address |  |  | Steering Committee and Management Committee
2. Overall status of the project
Overall status of the project |  |  | V |  | Compliance with quality |  |  |  | V |  |  | Legend:
[5 empty] | Risks |  |  |  | V |  | V | Under-control
Compliance with schedule |  |  | V |  | Team status |  |  |  | V |  | J | Required actions
Compliance with budget |  |  | V |  | Results indicators |  |  |  | V |  | R | Major problem
3. Work done during the last period
Description of activities carried out during the last period | [11 empty] | Date
End-of-month closing December 2021 and end-of-year closing 2021 | [11 empty] | 2022-01-09
User support and correction of minor issues | [11 empty] | The whole month of January
Special meetings and documentation of lessons learned during the project | [11 empty] | 2022-01-15
Official closing meeting | [11 empty] | 2022-01-29
4. Scheduled work for the next period
Description of the activities that remain to be done | [11 empty] | Predicted date
Project report | [11 empty] | 2022-01-29
Documentation finalization | [11 empty] | 2022-01-29
Final steering committee | [11 empty] | 2022-02-08
5. Outstanding item (s) and concern (s)
One of the main reasons for this project was to protect it from old systems controls . The project committee suggests to ask for our internal auditors support ,while conducting a detailed assessment of the capabilities and consistency of the SAP system used in CMRL. This should allow us to validate the compliance of our implementation and improve the consistency and quality of the data. If a correction is needed, the report would allow us to know in detail the settings to be adapted as a priority and thus avoid any problems during subsequent checks.
PROGRESS REPORT (2/2)
6. Outstanding item (s) resolved since the last report
The last data corrections identified have been carried out successfully. The few improvements identified for the closure have also been implemented. There remains a list of 4 minor corrections which have been communicated to the Center of Excellence and which are in the process of being corrected.
7. Progress status (current : 28-July 2022)
Project bundle |  |  | Budget at completion (BAC) | Planned value (PV) | Actual cost (AC) | % progress |  | Earned value (EV) |  | Schedule Variance (SV) |  | Cost variance (CV) |  | IPC |  | DPI
Expression of needs |  |  | 20000 | 20000 | 19500 | 100% |  | 19500 |  | -500 |  | 0 |  | 1 |  | 0.975
Planning |  |  | 36000 | 36000 | 36000 | 100% |  | 36000 |  | 0 |  | 0 |  | 1 |  | 1
Financial settings and tests |  |  | 24000 | 8000 | 8000 | 100% |  | 8000 |  | 0 |  | 0 |  | 1 |  | 1
Configuration and tests Sales |  |  | 24000 | 8000 | 8000 | 100% |  | 8000 |  | 0 |  | 0 |  | 1 |  | 1
Purchasing configuration and tests |  |  | 24000 | 8000 | 8000 | 100% |  | 8000 |  | 0 |  | 0 |  | 1 |  | 1
Logistics configuration and testing |  |  | 24000 | 8000 | 8000 | 100% |  | 8000 |  | 0 |  | 0 |  | 1 |  | 1
Configuration and production tests |  |  | 6000 | 2000 | 2000 | 100% |  | 2000 |  | 0 |  | 0 |  | 1 |  | 1
Master Data preparation |  |  | 16000 | 4000 | 4000 | 100% |  | 4000 |  | 0 |  | 0 |  | 1 |  | 1
User training |  |  | 7500 | 0 | 0 | 100% |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Operational switchover |  |  | 54500 | 0 | 0 | 100% |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
User support |  |  | 45000 | 0 | 0 | 100% |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Closing November 2021 |  |  | 16000 | 0 | 0 | 200% |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Operational support |  |  | 24000 | 0 | 0 | 300% |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Closing December 2021 |  |  | 12000 | 0 | 0 | 400% |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Documenting lessons learned |  |  | 8000 | 0 | 0 | 500% |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Project closure |  |  | 5000 | 0 | 0 | 600% |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
- |  |  | 0 | 0 | 0 | 700% |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total project |  |  | 346000 | 94000 | 93500 | 100% |  | 93500 |  | -500 |  | 0 |  | 1 |  | 0.99468
Analysis of variances and corrective actions:
No corrective action: the project is closed on time and on budget.
Monitoring of project deliverables:
Project deliverables |  |  | Type of deliverable | Member | Description |  | Lot | % progress | Delivery deadline | Validator |  |  |  |  | Validated version | Comment
Study of Opportunity |  |  | Decision support | Chantal / Olivier | Justification of the project and its importance in the business strategy |  | Lot 0 | 100% | 2021-04-09 | Board of directors |  |  |  |  | 1.3
Project charter |  |  | Initiation | Chantal / Olivier / Coordinators | Detailed project charter including deadlines and estimated costs |  | Lot 0 | 100% | 2021-04-29 | Board of directors | Comité de direction | 44316 | 44296
Schedule macro |  |  | Initiation | Chantal / Olivier / Coordinators | Estimation of the main phases |  | Lot 0 | 100% | 2021-04-29 | Board of directors | Comité de direction | 44316 | 44297 |  | 1.2
Kick-off meeting support Planning | Planification |  | Planning | Chantal | Presentation of the project to the team as soon as the charter is approved |  | Lot 1 | 100% | 2021-04-29 | Board of directors | Comité de direction | 44316 | 44298
Expression of needs |  |  | Planning | Chantal / Olivier / Coordinators | Summary of needs expressed during discovery meetings |  | Lot 1 | 100% | 2021-06-29 | Integrator / Sponsor | Sponsor / intégrateur | 44377 | 44299
Requirements matrix Planning | Planification |  | Planning | Chantal / Olivier / Coordinators | Collecting different requirements of key stakeholders |  | Lot 1 | 100% | 2021-06-29 | Integrator / Sponsor | Sponsor / intégrateur | 44377 | 44299
Specifications Planning | Planification |  | Planning | Chantal / Olivier / Coordinators | Detailed report of project expectations |  | Lot 1 | 100% | 2021-06-29 | Board of directors | Comité de direction | 44377 | 44301
Project plan Planning | Planification |  | Planning | Chantal / Olivier / Coordinators | Detailed plan of all planning aspects of the project |  | Lot 1 | 100% | 2021-06-29 | Board of directors | Comité de direction | 44377 | 44301
Workload program | Planification |  | Planning | Chantal / Olivier / Coordinators | List of tasks to be performed and estimate of the workload of the resources |  | Lot 1 | 100% | 2021-06-29 | Board of directors | Comité de direction | 44377 | 44301
Problem and risk register Planning | Planification |  | Planning | Chantal / Olivier / Coordinators | Scrupulous monitoring of risks and problems |  | Lot 1 | 100% | 2021-06-29 | Integrator / Sponsor | Sponsor / intégrateur | 44377 | 44304
Stakeholder register Planning | Planification |  | Planning | Chantal / Olivier / Coordinators | This register is the basis of successful communication |  | Lot 1 | 100% | 2021-06-29 | Integrator / Sponsor | Sponsor / intégrateur | 44377 | 44304
Competency matrix | Planification |  | Planning | Chantal / Olivier / Coordinators | Do we have the necessary skills in our teams? |  | Lot 1 | 100% | 2021-06-29 | Integrator / Sponsor | Sponsor / intégrateur | 44377 | 44304
Communication plan | Planification |  | Planning | Chantal / Olivier / Coordinators | An essential document which execution must be closely monitored. Don't forget the feedback. |  | Lot 1 | 100% | 2021-06-29 | Board of directors | Comité de direction | 44377 | 44307
Actions tracking | Planification |  | Planning | Chantal / Olivier / Coordinators | Visualize what remains to be done |  | Lot 1 | 100% | 2021-06-29 | Integrator / Sponsor | Sponsor / intégrateur | 44377 | 44308
Project deliverable monitoring | Planification |  | Planning | Chantal / Olivier / Coordinators | Are we respecting the scope and deadlines? |  | Lot 1 | 100% | 2021-06-29 | Integrator / Sponsor | Sponsor / intégrateur | 44377 | 44308
Change Requests Register | Réalisation |  | Execution | Chantal / Coordinators | What has changed since the project charter? Any change must be approved by the project committee and / or the steering committee. |  | Lot 2 | 100% | 2021-07-15 | Sponsor / Communication | Sponsor / Communication | 44392 | 44310
Budget monitoring | Rapports |  | Reports | Chantal | Project progress indicators |  | Lot 2 | 100% | 2021-07-15 | Sponsor / Communication | Sponsor / Communication | 44392 | 44311
Project dashboard | Rapports |  | Reports | Chantal | Regular detailed report on the project progress |  | Lot 2 | 100% | 2021-07-15 | Sponsor / Communication | Sponsor / Communication | 44392 | 44312
Flash Report | Rapports |  | Reports | Chantal | Indicators summarized on a single page |  | Lot 2 | 100% | 2021-07-15 | Sponsor / Communication | Sponsor / Communication | 44392 | 44313
Technical committee minutes Reports | Rapports |  | Reports | Rotating team member | Each meeting should be documented: who was present and what decisions were made? |  | Lot 2 | 100% | 2021-07-02 | Sponsor / Communication | Sponsor / Communication | 44392 | 44314
Project committee minutes Reports | Rapports |  | Reports | Rotating team member | Each meeting should be documented: who was present and what decisions were made? |  | Lot 2 | 100% | 2021-07-02 | Sponsor / Communication | Sponsor / Communication | 44392 | 44315
Steering committee minutes Reports | Rapports |  | Reports | Chantal | Each meeting should be documented: who was present and what decisions were made? |  | Lot 2 | 100% | 2021-07-02 | Sponsor / Communication | Sponsor / Communication | 44392 | 44316
IT infrastructure | Informatique |  | IT science | Daniel | The computer network and servers must be able to support the load of additional users and data. |  | Lot 2 | 100% | 2021-06-29 | Project team / Integrator / Sponsor | Equipe projet / Intégrateur / Sponsor | 44378 | 44317
Finance proof of concept | PoC |  | PoC | Monique | A very small solution to prove that everything will work as expected. |  | Lot 2 | 100% | 2021-07-15 | Integrator | Intégrateur | 44392 | 44318
Proof of concept sales | PoC |  | PoC | Denise | A very small solution to prove that everything will work as expected. |  | Lot 2 | 100% | 2021-07-15 | Integrator | Intégrateur | 44392 | 44318
Procurement Proof of Concept | PoC |  | PoC | Jean | A very small solution to prove that everything will work as expected. |  | Lot 2 | 100% | 2021-07-15 | Integrator | Intégrateur | 44392 | 44318
Logistics Proof of Concept | PoC |  | PoC | Eric | A very small solution to prove that everything will work as expected. |  | Lot 2 | 100% | 2021-07-15 | Integrator | Intégrateur | 44392 | 44318
Proof of concept Production |  |  | PoC | Georges | A very small solution to prove that everything will work as expected. |  | Lot 2 | 100% | 2021-07-15 | Integrator | Intégrateur | 44392 | 44318
Master Data proof of concept | PoC |  | PoC | Juliette | A very small solution to prove that everything will work as expected. |  | Lot 2 | 100% | 2021-07-15 | Integrator | Intégrateur | 44392 | 44318
Finance unit configuration and testing |  |  | Finance | Monique | Implementation: the heart of our project |  | Lot 2 | 100% | 2021-09-29 | Key-users | Utilisateurs-clés | 44468 | 44324
Unit configuration and testing Sales |  |  | Sales | Denise | Implementation: the heart of our project |  | Lot 2 | 100% | 2021-09-29 | Key-users | Utilisateurs-clés | 44468 | 44324
Purchasing unit configuration and testing |  |  | Purchases | Jean | Implementation: the heart of our project |  | Lot 2 | 100% | 2021-09-29 | Key-users | Utilisateurs-clés | 44468 | 44324
Logistics unit configuration and testing |  |  | Logistics | Eric | Implementation: the heart of our project |  | Lot 2 | 100% | 2021-09-29 | Key-users | Utilisateurs-clés | 44468 | 44324
Production unit configuration and testing |  |  | Production | Georges | Implementation: the heart of our project |  | Lot 2 | 100% | 2021-09-29 | Key-users | Utilisateurs-clés | 44468 | 44324
Financial integration and consolidation tests and corrections |  |  | Finance | Monique | Here, the solutions are tested and validated by our key users. |  | Lot 2 | 100% | 2021-10-29 | Key-users | Utilisateurs-clés | 44468 | 44324
Integration and consolidation tests and corrections Sales |  |  | Sales | Denise | Here, the solutions are tested and validated by our key users. |  | Lot 2 | 100% | 2021-10-29 | Key-users | Utilisateurs-clés | 44468 | 44324
Purchasing integration and consolidation tests and corrections |  |  | Purchases | Jean | Here, the solutions are tested and validated by our key users. |  | Lot 2 | 100% | 2021-10-29 | Key-users | Utilisateurs-clés | 44468 | 44324
Logistics integration and consolidation tests and corrections |  |  | Logistics | Eric | Here, the solutions are tested and validated by our key users. |  | Lot 2 | 100% | 2021-10-29 | Key-users | Utilisateurs-clés | 44468 | 44324
Integration and consolidation tests and corrections Production |  |  | Production | Georges | Here, the solutions are tested and validated by our key users. |  | Lot 2 | 100% | 2021-10-29 | Key-users | Utilisateurs-clés | 44468 | 44324
Master Data integration and consolidation tests and corrections |  |  | Master Data | Juliette | Here, the solutions are tested and validated by our key users. |  | Lot 2 | 100% | 2021-10-29 | Key-users | Utilisateurs-clés | 44468 | 44324
Productive environment Finances |  |  | Finance | Monique | We deploy validated solutions |  | Lot 3 | 100% | 2021-11-26 | Key-users | Utilisateurs-clés | 44468 | 44324
Productive environment Sales |  |  | Sales | Denise | We deploy validated solutions |  | Lot 3 | 100% | 2021-11-26 | Key-users | Utilisateurs-clés | 44468 | 44324
Productive environment Purchasing |  |  | Purchases | Jean | We deploy validated solutions |  | Lot 3 | 100% | 2021-11-26 | Key-users | Utilisateurs-clés | 44468 | 44324
Productive environment Logistics |  |  | Logistics | Eric | We deploy validated solutions |  | Lot 3 | 100% | 2021-11-26 | Key-users | Utilisateurs-clés | 44468 | 44324
Productive environment Production |  |  | Production | Georges | We deploy validated solutions |  | Lot 3 | 100% | 2021-11-26 | Key-users | Utilisateurs-clés | 44468 | 44324
Data migration |  |  | Master Data | Juliette | The cleaned and corrected data is fed into the new system |  | Lot 3 | 100% | 2021-11-27 | Key-users | Utilisateurs-clés | 44468 | 44324
Finance training |  |  | Finance | Monique | We deploy the documentations by theme and we train ALL users |  | Lot 4 | 100% | 2021-11-26 | Change | Changement | 44526 | 44341
Sales training |  |  | Sales | Denise | We deploy the documentations by theme and we train ALL users |  | Lot 4 | 100% | 2021-11-26 | Change | Changement | 44526 | 44341
Purchasing training |  |  | Purchases | Jean | We deploy the documentations by theme and we train ALL users |  | Lot 4 | 100% | 2021-11-26 | Change | Changement | 44526 | 44341
Logistics training |  |  | Logistics | Eric | We deploy the documentations by theme and we train ALL users |  | Lot 4 | 100% | 2021-11-26 | Change | Changement | 44526 | 44341
Production training |  |  | Production | Georges | We deploy the documentations by theme and we train ALL users |  | Lot 4 | 100% | 2021-11-26 | Change | Changement | 44526 | 44341
Receipt of deliverables |  |  | Test | Juliette | All deliverables are subject to an official Receipt |  | Lot 5 | 100% | 28-11-211 | Integrator / Sponsor | Intégrateur / Sponsor | 28-11-211 | 44346
Tilting |  |  | Start-up | Project team and all users | Last validation before operational start. Exceptional steering committee. |  | Lot 5 | 100% | 2021-11-28 | Integrator / Sponsor | Intégrateur / Sponsor | 28-11-212 | 44347
Starting the new system |  |  | Start-up | Project team and key users | Start-up and user observation / support |  | Lot 5 | 100% | 2021-11-29 | Steering committee | Comité de pilotage | 44529 | 44348
Test book |  |  | Test | Chantal / Olivier / Jacques | The whole project is approved after a period of real treatments |  | Lot 5 | 100% | 2021-11-30 | Steering committee | Comité de pilotage | 44529 | 44348
Closing meeting |  |  | Closure | TOUS | The closing meeting takes place in two stages: a gathering of all in order to document what remains to be done and what are the lessons learned - and a much less formal part to celebrate the success of the project and declare it finished. |  | Lot 5 | 100% | 2022-01-29 | ALL | TOUS | 44590 | 44350
Project closure report |  |  | Closure report | Chantal / Olivier / Jacques / Coordinators | We document here the lessons learned and we make one last point. This document will be archived for future reference. |  | Lot 5 | 100% | 2022-02-15 | Steering committee | Comité de pilotage | 44607 | 44351
8. Risk monitoring
No. | Risks / opportunities | Impact | Probabilities | Weight | Preventive measures |  |  |  | Risk evolution |  | Risk status |  |  |  |  | Risk monitoring
1 | Negative audit | Average | low | 2 | Ask internal auditors to validate the new system in detail - with a focus on data quality |  |  |  | Stable |  | Open risk |  |  |  |  | Project manager and sponsor
2 | Old contracts | Low | low | 1 | Recheck if that old systems contracts are canceled to avoid unnecessary payment |  |  |  | Decrease |  | Open risk |  |  |  |  | IT manager
3 | [10 empty] | Open risk
4 | [10 empty] | Open risk
9.Lessons Learned and Recommendations
The project manager and his team compile the lessons learned during the project and present recommendations for similar projects:
Field |  |  |  | Lessons learned |  |  |  |  | Recommendations
Communication |  |  |  | Importance of considering stakeholder perspective |  |  |  |  | Survey all staff and understand perceptions of the project
|  |  |  | The intranet is not accessible by / for everyone |  |  |  |  | Use ALL information signs, including inside and outside the factory
|  |  |  | Do not neglect the post-project |  |  |  |  | Schedule subsequent communications for at least three months
Content and integration |  |  |  | An assembly plant is administratively and functionally more complex |  |  |  |  | Keep all documentation of this project for the next SAP upgrade planned for next year
Purchases / Contracts |  |  |  | Big differences between small / medium and very large customers |  |  |  |  | The new settings should make it possible to face this challenge
Costs |  |  |  | Importance of anticipating the unforeseeable |  |  |  |  | Provide a safety cushion of 5 to 10%
Deadline |  |  |  | Holidays are sacred |  |  |  |  | Provide emergency resources
Quality |  |  |  | Sometimes poor data quality |  |  |  |  | Do a quality pre-study and do not underestimate the impact
Human resources |  |  |  | Absenteeism is not an exact science |  |  |  |  | Provide for the rapid replacement of sick or excused people
Risk |  |  |  | Regular risk review is essential |  |  |  |  | Never remove this review from the meeting agenda
Technologies |  |  |  | Imperfect inventories |  |  |  |  | Do not forget about the corners furthest from the assembly center. Update inventory
Diverse |  |  |  | Training materials must be tailor-made |  |  |  |  | Validate training materials by key users