## Project report
Project closure report
1. PROJECT IDENTIFICATION
Name /Project Code |  |  | SAP30/CMRL |  |  |  |  | Creation date |  | 2022-01-14
Reference |  |  | Strategy 2022/CMRL |  |  |  |  | Version date |  | 2022-01-28
Project manager |  |  | Chantal Dupont |  |  |  |  | Version N° |  | V2.3
Service/Organization |  |  | Confassis S.A.
Documents attached to this report:
Acceptance test book and minutes of the Final Steering Committee.
2. GAP ANALYSIS
Were the deliverables delivered as planned in the project charter?
Yes/No: | Yes | Comment
The project is a success and the deliverables have been delivered as provided in the charter. This includes CRM applications. It is important to note that the CRM applications were released at the end of December for use from January 2022.
Have the project objectives, as defined in the project charter, been achieved?
Yes/No: | Yes | Si not, explain:
All the objectives were achieved in terms of quality, scope and budget. It will be necessary to wait for the complete decommissioning of the old systems before being able to benefit from all the advantages of the new solutions. This is ongoing and nothing prevents achieving full returns on investments.
Has the project end date, as estimated in the basic planning of the project management plan, been respected?
Yes/No: | Yes | If not, indicate the initial date and the actual closing date of the project and explain:
The project had an initial date of November 29, 2022 for the system failover. A plan B had been developed for a changeover in December in case of any major problem. This back-up plan was not necessary and we delivered on the date originally planned.
Has the cost of the project, as estimated in the basic planning of the project management plan, been respected?
Yes/No: | Yes | If not, indicate the initial cost and the actual cost of closing the project and give some explanations:
The scope and start date having been respected, the cost of the project was also respected. It should be noted that some workstations had to be updated, and this was done by the IT department and charged to the infrastructure budget . These positions had been forgotten during the last update of the IT equipment.
Have the project efforts (in d-h), as estimated in the basic planning of the project management plan, been respected?
Yes/No: | No | If not, indicate the estimated initial efforts of the project and the actual efforts and explain these differences:
The Master Data part of the project was more difficult than expected and the corrections extremely important. The workload of the Master Data team was exceeded by 5%. However, these additional efforts did not have a negative effect on the budgets because the members assigned to corrections and support, had less work than expected for day-to-day management.
3. FEEDBACK ON THE RISK ANALYSIS
The project manager and his team comment on the risks that arose during the project:
Risks |  |  |  | Planned impact |  |  | Real impact
Poor data quality |  |  |  | Master Data resource assignment |  |  | Corrections much larger than expected
Significance of fixed assets |  |  |  | Little impact |  |  | Significant migration. Multiple rules
Communication challenges |  |  |  | Need for a change manager |  |  | Very many stakeholders, sometimes unidentified
Use of headquarters servers |  |  |  | Sufficient servers |  |  | Need to put in place the contingency plan
Workstations to be replaced |  |  |  | Park up to date |  |  | A few posts had been forgotten. Problem corrected
4. UNEXPECTED IMPACTS
The project manager and his team comment on the risks highlighted during the project and that were not planned:
Higher than normal absenteeism forced us to allocate reserve resources during the setup period. Fortunately, the teams at the headquarters' competence center were able to delegate specialists very quickly, thus reducing the impact of the problem.
5. POST IMPLEMENTATION STAGE
Some errors were detected during the November close. These issues were immediately corrected and the December close went off without any issue.
6.LESSONS LEARNED AND RECOMMENDATIONS
The project manager and his team compile lessons learned during the project lifecycle, and present recommendations for similar projects:
Field |  |  | Lessons learned |  |  |  | Recommendations
Communication |  |  | Importance of considering stakeholder perspective |  |  |  | Survey all staff and understand perceptions of the project
|  |  | The intranet is not accessible by / for everyone |  |  |  | Use ALL information signs, including inside and outside the factory
|  |  | Do not neglect the post-project |  |  |  | Schedule subsequent communications for at least three months
Content and integration |  |  | An assembly plant is administratively and functionally more complex |  |  |  | Keep all documentation of this project for the next SAP upgrade planned for next year
Purchases / Contracts |  |  | Big differences between small / medium and very large customers |  |  |  | The new settings should make it possible to face this challenge
Cost |  |  | Importance of anticipating the unforeseeable |  |  |  | Provide a safety cushion of 5 to 10%
Deadline |  |  | Holidays are important |  |  |  | Provide emergency resources
Quality |  |  | Sometimes poor data quality |  |  |  | Do a quality pre-study and do not underestimate the impact
Human resources |  |  | Absenteeism is not an exact science |  |  |  | Provide for the rapid replacement of sick or excused people
Risks |  |  | Regular risk review is essential |  |  |  | Never remove this review from the meeting agenda
Technologies |  |  | Imperfect inventories |  |  |  | Do not forget about the corners furthest from the assembly center. Update inventory
Various |  |  | Training materials must be tailor-made |  |  |  | Validate training materials by key users
7. STAKEHOLDER SATISFACTION
Rate and comment in this section, the satisfaction of the stakeholders. You can set a rating on a scale of 1 to 5 as an example, then interview the different stakeholders to rate their levels of satisfaction with the (x): -Progress of the project -Results achieved
Stakeholder |  |  |  | Criterion 1 (communication) | Criterion 2 (respect of deadlines) | Criterion 3 (Quality of deliverables) |  | Criterion 4 | Satisfaction (Medium)
Stakeholder 1 |  |  |  | 4 | 2 | 4 |  | 5 | 3.75
Stakeholder 2 |  |  |  | 3 | 3 | 5 |  | 3 | 3.5
Stakeholder 3 |  |  |  | 2 | 4 | 4 |  | 4 | 3.5
Stakeholder 4 |  |  |  | 3 | 3 | 3 |  | 5 | 3.5
Stakeholder 5 |  |  |  | 3 | 4 | 4 |  | 3 | 3.5
[6 empty] | General satisfaction: |  |  | 3,55/5
Comment :
8. SUBMISSION OF PROJECT DOCUMENTS
Check that all documents relating to the project have been submitted. If not, explain why.
Type of documents |  |  |  |  | Archived? |  | Comments
Study of Opportunity |  |  |  |  | X
Project charter |  |  |  |  | X
Specifications |  |  |  |  | X
Project management plan: initial version and later versions |  |  |  |  | X
Progress reports |  |  |  |  | X
Meeting minutes |  |  |  |  | X
Follow-up reports |  |  |  |  | X
Problem and risk register |  |  |  |  | X
Register of deliverables |  |  |  |  | X
Risk register |  |  |  |  | X
Tests book |  |  |  |  | X
Project report | [6 empty] | To be approved by the steering committee
Closing report | [6 empty] | To be approved by the steering committee
Other relevant documents
Tests Strategy and Tests book
9. PROJECT CLOSURE
The stakeholders confirmed the reception of the deliverables in compliance with the expectations of the project. The support team has been defined and trained. The project is deemed to be completed. Consequently, the operations accept the closure of the project for switching to RUN.