## Workflow Gestion de Projet
Plan, implement and control the change
YES
NOGO
Rejection
Kick off
Setting project
expectations
Planning
Activities, resources,
planning and costs
Execution
Project plan roll-out and deliverables acceptance
Control
Monitoring and evaluation
Change request
Closing
Checking project goals achievement
Enter the
maintenance phase
(RUN mode)
* Craft a residual backlog (Remaiing scope to be done)
Parallel phases
NO
YES
NON
NO
YES
Feasability T.E.L.O.S Delivrables
- Technical Feasability and opportunity study
- Economic
- Legal
- Organizationnal
- Scheduling
Feasability study
Need or Opportunity
Project management: Waterfall method
Project Governance (Decision-making)
Strategic committee or Executive committee
Feasible and viable project?
Deliverables compliant to the project plan?
Is the project approved? Is there anything left to do?
Delivrables Governance bodies
- Project charter Kick off meeting (could be the 1st steering committee)
- 1st stakeholders analysis
- 1st Risk analysis
- Macro planning
Delivrables Governance bodies
- Project Management Plan Steerco (Steering committee)
- Detailed project scope statement Project committee
- WBS
- Detailed planning
- Communication plan
- Quality assurance plan
...
Delivrables Governance bodies
- Action monitoring Steerco
- Deliverable monitoring Project committee
- Acceptance strategy Technical committee
- Test plan
Delivrables Governance bodies
- Risk control Steerco
- Progress monitoring (Earned value) Project committee
- Project dashboard Technical committee
- Control of change requests
Delivrables Governance bodies
- Project documentation Project closure report
- Deliverable acceptance receipt Post mortem meeting
- Approved acceptance receipt
- Project closure report
- SLA contract (Service Level Agreement)
- RACI matrix
- Change requests register
- Monitoring report
- *residual backlog (Remains to be done)